## ProjectTeam
Name | GitHub Alias | Role
Füglister Robin | fuglr3 | Scrum Master
Schläppi Mario | schlm8 | Developer
Luginbühl Ramon | RamonLuginbuehl | Developer
Beyeler Luca | beyel3 | Developer
Künzler Urs | UrsKuenzler | Product Owner
Vogel Jürgen | vgj1 | Product Owner

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original [h] | Effort Plan Updated [h] | Effort Actual | Status
1 | User Login | User logs in with existing credentials and the landing page is displayed. | high | 8h | 6h | 6h | done
2 | Add Account (create) | A new useraccount is created either by user (relative / patient) or by admin. | low | 6h | 6h | 6h | done
3 | Create new event (public / private) | The user (relative account) creates a new event. The system generates a new event template. The user fills in the necessary data and decides if the event is public or private. | high | 23h | 23h | 21h | work in progress
4 | Filter / search event template in database | The user (relative account) filters the event template database part and searches an event template via the "search event template" mask. | high | 18h | 8h | 8h | done
5 | Create event out of template | The user ceates an event instance out of the selected template. | high | 4h | 4h | 3h | work in progress
6 | Send / accept friend request | The user (relative) searches for patients and sends a friend request to a patient. | high | 8h | 8h | 1h | work in progress
7 | Add a patient to an event | The owner of the event adds a patient in his freindlist to the event. | high | 4h | 4h | 0h | work in progress
8 | Mark Event done | After completing the Event (activity outside our app), the owner marks the event as done using the "complete Event" mask. He uploads a photo (optional) and gives a rating. | medium | 15h | 15h | 3h | work in progress
9 | Check my events | The user looks at the overview of his created/participated events. | medium | 4h | 4h | 2h | work in progress
10 | Search public event and participate | The user searches for public events via the "search Event" mask. He picks one and participates in it. | medium | 10h | 10h | 2h | work in progress
11 | Use Chat | Once an event is created, the user uses the chat to communicate with other participants. | low | 6h | 6h | 2h | work in progress
12 | Check patient's events / info | The user (relative) checks the open events of another user (patient) and can see the patient's general information. Accessible via "search patient" mask on landing page and event creation mask. | low | 4h | 4h | 0h | waiting
13 | Administration via admin account | User logs in with an admin account. Additional functionalities are provided (change account passwords, create new accounts). | low | 2h | 2h | 1h | work in progress
| Available work hours: | 112 h

## Sprint1 Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Event Template Model | Basic model implementation, 2 hard coded instances of previously developed basic implementation | All | Mario | Robin | high | 2h | 2h | 2h | done
1.2 | 1 | Event Model | Basic model implementation, 2 hard coded instances of previously developed basic implementation | All | Mario | Robin | high | 2h | 2h | 2h | done
1.3 | 1 | Persistence Design | Database design with tables, columns and datataypes | Database | Robin | Mario | high | 2h | 2h | 1h | done
1.4 | 1 | Persistence Implementation | Implementation and Authentication | Database | Robin | Mario | high | 2h | 2h | 2h | done
1.5 | 1 | Persistence search and filter | Basic search and filter functions to provide data to presenters | Database | Robin | Mario | low | 2h | 2h | 2h | done
1.6 | 1 | Persistence save and load | Basic save and load functions to write and read from database | Database | Robin | Mario | high | 2h | 2h | 3h | done
1.7 | 1 | Account Model | Implementation of the basic account model | All | Ramon | Luca | high | 1h | 1h | 1h | done
1.8 | 1 | Account Model subclasses | Subclasses created form the basic account model for Relative and Patient | All | Ramon | Luca | medium | 1h | 1h | 1h | done
1.9 | 1 | Account Model testing | 4 hardcoded accounts for developement purposes (2 Relatives, 2 Patients) | Database | Ramon | Luca | low | 1h | 1h | 1h | done
1.1 | 1 | MainView | Implementation of the main UI elements | UI | Luca | Ramon | high | 4h | 5h | 5h | done
1.11 | 1 | MainView Presenter | Implementation of the MainView presenter to manage numerous views | UI, Presenter | Luca | Ramon | high | 4h | 0h | 0h | cancelled
1.12 | 1 | EventCreaterView | Implementation of the CreateEvent UI Elements | UI | Mario | Robin | medium | 2h | 5h | 5h | done
1.13 | 1 | EventSearchView | Implementation of the EventSearch UI Elements | UI | Ramon | Robin | medium | 2h | 2h | 2h | done
1.14 | 1 | EventPresenter & EventCreater Implementation | Implementation of the CreateEventPresenter to manage EventCreaterView | UI, Presenter | Mario | Luca | high | 2h | 2h | 2h | done
1.15 | 1 | EventPresenter & EventSearch Implementation | Implementation of the CreateEventPresenter to manage EventSearchView | UI, Presenter | Ramon | Luca | high | 2h | 2h | 2h | done
1.16 | 1 | coreUser Interface | Implementation of the CoreUser interface | All | Ramon | Luca | high | 1h | 1h | 1h | done
1.17 | 1 | MainLayout | Implementation of the MainLayout elements wich are used for all views | UI, Presenter | Luca | Ramon | medium | 4h | 4h | 4h | done
[7 empty] | s1 = 8h / pers. |  | 32h
[7 empty] | s2 = 14h / pers. |  | 56h
[7 empty] | s3 = 6h / pers. |  | 24h

## Sprint2 Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
2.1 | 2 | Account Login | Implementation of the login logic with DB connection | All | Ramon | Robin | high | 2h | 2h | 2h | done
2.2 | 2 | Account SignUp | Implementation of the sign up logic to create a new account and saving the account into the DB | All | Ramon | Robin | medium | 4h | 4h | 4h | done
2.3 | 2 | Account SingUp View | Implementation of the SingUp UI elements | UI, Presenter | Ramon | Robin | medium | 2h | 2h | 2h | done
2.4 | 2 | Relate Events to Account | Implementation of the functionality to relate an event with specific accounts | All | Ramon | Robin | high | 2h | 2h | 1h | work in progress
2.5 | 2 | AccountView | Implementation of the MyEvent UI Elements | UI, Presenter | Luca | Mario | high | 2h | 2h | 2h | work in progress
2.6 | 2 | AccountPresenter | Implementation of the MyEvents presenter to manage the MyEvents View | UI, Presenter | Mario | Luca | high | 2h | 4h | 0h | work in progress
2.7 | 2 | Task 08 Persistance | Revision and extention of the class diagram to include persistence | Database | Robin | Mario | high | 4h | 4h | 4h | done
2.8 | 2 | Friend Request | Implementation of the friend request logic to relate a patient with a relative with UI elements | All | Robin | Ramon | medium | 2h | 2h | 1h | work in progress
2.9 | 2 | DB Refactoring | Discuss potential changes to set the logic for the persistance on the models and not in a single class | All | Robin | Ramon | low | 1h | 1h | 1h | done
2.1 | 2 | Add Patient to Event | Implementation of the logic to give a relative account the funtionality to add a patient to an event | All | Mario | Luca | medium | 2h | 2h | 0h | cancelled
2.11 | 2 | Search / Filter Templates | Implementation of the search / filter logic for the event templates with UI elements | All | Luca | Mario | medium | 4h | 4h | 4h | done
2.12 | 2 | Search Public Events | Beginning of implementation of the search logic to find public event executions | All | Robin | Luca | medium | 2h | 2h | 0h | work in progress
2.13 | 2 | Search Public Events View | Implementation of the Search Public Events UI elements | UI, Presenter | Luca | Robin | medium | 1h | 1h | 0h | work in progress
2.14 | 2 | MVP Refactoring | Refactoring of several classes to match the MVP pattern | All | All | All | high | 4h | 10h | 10h | done
2.15 | 2 | EventCreaterPresenter & EventCreater Implementation | Completition of the event creation functionality | All | Mario | Luca | high | 4h | 4h | 4h | work in progress
2.16 | 2 | UI Revision | Revision of the UI Elements to match the new functionalities | UI, Presenter | Luca | Mario | low | 2h | 2h | 2h | done
2.17 | 2 | PostView | Implementation of the Chat UI elements | UI, Presenter | Luca | Mario | medium | 1h | 1h | 1h | done
2.18 | 2 | PostPresenter & Model | Implementation of the Chat presenter to manage the ChatView | UI, Presenter | Mario | Luca | medium | 2h | 2h | 0h | work in progress
2.19 | 2 | Post Persistance | Expantion of the database to save and load chats | Database | Robin | Ramon | medium | 1h | 1h | 1h | done
[7 empty] | s1 = 8h / pers. |  | 32h
[7 empty] | s2 = 14h / pers. |  | 56h
[7 empty] | s3 = 6h / pers. |  | 24h

## Sprint3 Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
3.1 | 3 | [5 empty] | high |  |  |  | waiting
3.2 | 3 | [5 empty] | high |  |  |  | waiting
3.3 | 3 | [5 empty] | high |  |  |  | waiting
3.4 | 3 | [5 empty] | high |  |  |  | waiting
3.5 | 3 | [5 empty] | high |  |  |  | waiting
3.6 | 3 | [5 empty] | high |  |  |  | waiting
3.7 | 3 | [5 empty] | high |  |  |  | waiting
3.8 | 3 | [5 empty] | high |  |  |  | waiting
3.9 | 3 | [5 empty] | high |  |  |  | waiting
3.1 | 3 | [5 empty] | high |  |  |  | waiting
3.11 | 3 | [5 empty] | high |  |  |  | waiting
3.12 | 3 | [5 empty] | high |  |  |  | waiting
3.13 | 3 | [5 empty] | high |  |  |  | waiting
3.14 | 3 | [5 empty] | high |  |  |  | waiting
3.15 | 3 | [5 empty] | high |  |  |  | waiting
3.16 | 3 | [5 empty] | high |  |  |  | waiting
[7 empty] | s1 = 8h / pers. |  | 32h
[7 empty] | s2 = 14h / pers. |  | 56h
[7 empty] | s3 = 6h / pers. |  | 24h

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180

## DropDownItems
Status | Priority | Owner
waiting | high
work in progress | medium | Luca
done | low | Robin
cancelled |  | Ramon
Mario